Transition Process Timeline

Phase IV

MINISTERS

Recruitment Team vets candidates, narrows list, offers Vestry shortlist of finalists

Phase IV

MINISTERS

Receiving Names as Recruitment Team prepares interview questions & protocol

Phase I CHANGE Farewell & Preparation Transition Leadership Team: Interim Rector Transition Consultants

| 2-3 months | 1-2 months | 4-8 months | 2-3 months | 1-2 months | 1-2 months | 1-3 months |
| --- | --- | --- | --- | --- | --- | --- |

Phase V

NEW MINISTRY

Rector arrives & is welcomed

Phase IV

MINISTERS

Vestry interviews & calls new Rector

Phase III

MISSION & MINISTRY

Discernment Team leads conversations with parish, gathers data, develops Parish Profile, OTM/TMC Portfolios, and website content

Phase II REALITY

Address any systemic issues (e.g., conflict or finance) & select Team Members

Note: Each parish moves at its own pace and according to its own processes of discernment and recruitment. This timetable is suggested only as an aid in gauging progress and maintaining momentum

Note: Each parish moves at its own pace and according to its own process of discernment; this timetable is suggested only as an aid in gauging progress and holding to a certain schedule.